## Proforma
140K purchase 60K renovation |  | 1246 total sf, 2 bed 1 bath, 1956 |  | 275K ARV
Item |  | Cost |  | 1750 sf 2/2/1 |  |  | Rough Break Out
Purchase Price |  | 130000 |  |  |  |  | 500 sf Addition | 50000
Closing Cost |  | 4841.81 |  |  |  |  | Kitchen and Appliances | 8500
Prepaid Items |  | 2391 |  |  |  |  | Fence | 2000
Renovation |  | 105000 |  |  |  |  | Deck | 1500
1 month carrying cost |  | 1600 |  |  |  |  | Paint and trim | 1000
Down Payment (3.5%) (Total cash invested) |  | 7875 |  |  |  |  | Floor | 4000
Total closing and prepaid |  | 7232.81 |  |  |  |  | Shop floor/and lights | 2000
Mortgage Insurance |  | 2219 |  |  |  |  | Guest Bath | 1000
Seller Concession |  | 5500 |  |  |  |  | Windows | 5000
Bank Credit |  | 1527.5
Total Cash to close |  | 9607.81 | [5 empty] | 75000
Mortgage amount |  | 231149.31
PMIT |  | 1588.8333
ARV Sell price |  | 300000
6% closing and commision |  | 15000
Walk away cash |  | 53850.69
Profit |  | 45975.69
Closing Cost/Previous |  |  | Closing Cost Dec 13
Processing | 795 |  | Origination charge |  | 3090
Supplemental Origination | 500 |  | Credit Report |  | 13.25
Credit Report | 15 |  | Appraisal |  | 495
Title Closing Fee | 375 |  | Tax service fee |  | 78
Title Insurance | 820 |  | Flood Life of Loan fee |  | 19
HUD Consultant | 2000 |  | Title Ins Lend Cov |  | 360
Flood Certification | 19 |  | Endorsemet-Env Lien |  | 98.56
Recording Fee | 193 |  | Closing/Escrow/Settlement |  | 300
State Tax Stamp | 18.63 |  | Endorsment To title |  | 95
Inspection | 300 |  | Closing Protection Ltr |  | 35
Appraisal | 450 |  | Recording Fee Mrtg/Dot |  | 126
Total Closing Cost | 5485.63 |  | Recording Fee Deed |  | 16
|  |  | State Tax Stamp Deed |  | 16
|  |  | Courier/Msngr |  | 100
|  |  | Total Closing |  | 4841.81
|  |  | FHA Upfront MIP |  | 1795.86
Prepaid Items/Previous |  |  | Prepaid Items/Previous
15 days Interest | 307 |  | 15 days Interest |  | 307
Taxes (4 Months) | 666.6667 |  | Taxes (4 Months) |  | 1583
1st Year Premium Insurance + 3 months | 1562.5 |  | 1st Year Premium Insurance + 3 months |  | 1000
Total | 2536.1667 |  | Aggregrate Adjustment |  | 499
|  |  | Total |  | 2391
Total Closing and Prepaid Items | 8021.7967 | (Items to covered by seller concession)
Purchase Price ( 175K plus closing and prepaid items) | 138021.7967 |  |  |  |  | ww
Additional Items added to Loan
Up Front Mortgage Insurance | 2219

## Budget Final
Date 06/12/12
HUD Item # | Item Number | Item | QTY | Est. Labor Cost Per | Est. Labor Total | Est. Material Cost Per | Material Total | Item Budget Total | Total spent to Date 8/26/12 | Remaining Funds | Total Draw 1-6/12/12 (spent) | Total Draw 2-7/5/12 (spent) | Total Draw 3-8/26/12(spent) | HUD Budget | HUD/Actual difference | HUD draw % to date | HUD draw amount to date 7/5/12 | Hud Draw-1 6/12/12 | Hud Draw -2 7/5/12 | Hud Draw -3 8/26/12
35 |  | Disposal and Demolition |  |  | 0 |  | 300 | 300 | 127.87 | 172.13 | 0 | 128 |  | 300 | 0 | 0% |  |  | 0
35 | 1 | Roll Out (disposal) | 1 |  |  | 300 | 300 | 300 | 127.87 | 172.13 | 0 | 127.87 |  | 300 | - | 42.67% | 128 |  | 128
35 | 2 | Demolition (man/days) | 6 | 120 | 0 |  |  | 0 |  | 0 | 0 | 0 |  | - | -
17 |  | Professional Services |  |  | 950 |  |  | 950 | 950 | 0 | 950 | 0 |  | 950 | 0 | 100% | 950 | 950 | 0
17 | 3 | Engineering | 1 | 950 | 950 |  |  | 950 | 950 | 0 | 0 | 950 |  | - | -
1 |  | Foundation Concrete work, Excavation and backfill |  |  | 3000 | 800 | 1500 | 7854 | 7853.75 | 0.25 | 0 | 7854 |  | 2300 | -5554 | 100% | 2300 |  | 2300
1 | 4 | Addition Column 30''X30''X12'' CONC PAD w/ 16"x16" x 4' Pilasters | 14 | 255 | 3000 | 800 | 1500 | 7854 | 7853.75 | 0.25 | 0 | 7853.75 |  | - | -
17 |  | Wall Framing |  |  | 1600 |  | 19686.71 | 21286.71 | 18101.2 | 2922.51 | 9941 | 7900 | 260.2 | 15801 | -5485.71 | 100% | 15800.95 | 4580 | 10382.95 | 838
17 | 6 | (Ext) wall (847 SF)2x6 Framing,sheathing,insulation, tar paper, Mtpl; barnwood siding (SF) | 792 |  | 1600 |  | 7994 | 7994 | 5571.8 | 2422.2 | 2936 | 2548 | 87.8 | - | -
17 | 6.1 | (Ext) wall patch and tooth in siding where window is to be removed (SF) | 55 |  |  |  | 500 | 500 | 0 | 500 | 0 | 0 |  | - | -
17 | 6.2 | (Int) wall (330 sf); 2x4 Framing (SF) | 330 |  |  |  | 327 | 327 | 326.5 | 0.5 | 327 | -0.5 |  | - | -
17 | 7 | Timber Columns and Beams | 31 |  |  |  | 3518 | 3518 | 3518.09 | -0.09 | 3518 | 0 |  | - | -
17 | 9 | Column brackets (30),bases (14) and hardware |  |  |  |  | 3160 | 4497 | 4497.1 | -0.1 | 3160 | 1165 | 172.1 | -
17 | 9.2 | Floor framing - ICF |  |  |  |  | 4187.71 | 4187.71 | 4187.71 | 0 | 0 | 4187.71 |  | - | -
|  | Fireplace and Outdoor Kitchen |  |  | 0 |  | 11933.35 | 11933.35 | 3550.6 | 8527.75 | 3406 | 0 | 144.6 | 0 | -11933.35 |  |  |  | 0
| 10 | Fireplace box, and venting |  |  | 0 |  | 5827.35 | 5827.35 |  | 5827.35 | 0 | 0 |  | - | -
| 11 | Fireplace framing and stone | 100 | 10 |  | 8 | 1700 | 1700 |  | 1700 | 0 | 0 |  | - | -
| 12 | Outdoor kitchen concrete countertops (SF) | 35 |  |  | 10 | 0 | 0 |  | 0 | 0 | 0 |  | - | -
| 13 | Built in outdoor grill |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | - | -
| 14 | Exterior Deck Framing (SF) | 500 |  | 0 | 4 | 3406 | 3551 | 3550.6 | 0.4 | 3406 | 0 | 144.6 | -
| 15 | Railings (LF) | 60 | 16 |  | 20 | 1000 | 1000 |  | 1000 | 0 | 0 |  | - | -
300 |  | Windows & Door Install |  |  | 943 |  | 16330 | 17273 | 16073 | 1200 | 0 | 4800 | 11273 | 11075 | -6198 | 93.23% | 10325 | 4800 |  | 5525
13 and 15 | 16 | Windows and Exterior Doors | 15 |  | 643 |  | 15430 | 16073 | 16073 | 0 | 0 | 4800 | 11273 | 9875 | -6198 | 44.05% | 4350 | 4350 |  | 5225
16 | 19 | Interior Doors | 6 | 50 | 300 | 150 | 900 | 1200 |  | 1200 | 0 | 0 |  | 1200 | 0 | 37.5% | 450 | 450 |  | 300
18 |  | Drywall |  |  | 2825.375 |  | 1156.6111 | 3981.9861 | 33.19 | 3948.7961 | 0 | 33 |  | 3996 | 14.0139 |  |  |  | 0
18 | 21 | Walls and Ceilings (Hang Tape Mud per sheet) | 61.6389 | 27 | 1664.25 | 8 | 493.1111 | 2157.3611 | 33.19 | 2124.1711 | 0 | 33.19 |  | - | -
18 | 22 | Walls and Ceilings (Texture per sheet) | 165.875 | 7 | 1161.125 | 4 | 663.5 | 1824.625 |  | 1824.625 | 0 | 0 |  | - | -
31 |  | Cabinets |  |  | 0 |  | 8400 | 8400 | 280 | 6420 | 280 | 0 |  | 7589 | -811 | 49.35% | 3745 | 2745 |  | 1000
31 | 23 | Kitchen Cabinets and butcher block | 9.98 |  | 0 | 125 | 6000 | 6000 |  | 6000 | 0 | 0
31 | 25 | Quartz Countertops (LF) 44SF kitchen; 16 sf vanity | 60 |  |  | 40 | 2400 | 700 | 280 | 420 | 280 | 0
25 |  | Tile |  |  | 1530 |  | 1318 | 2848 | 0 | 2848 | 0 | 0 |  | 3048 | 200 | 0% | 0 |  | 0
25 | 26 | Shower Tile and shower pan (200SF) | 200 | 5 | 1000 | 5 | 1000 | 2000 |  | 2000 | 0 | 0 |  | - | -
25 | 27 | Floor Tile (SF) | 106 | 5 | 530 | 3 | 318 | 848 |  | 848 | 0 | 0 |  | - | -
20 |  | Finish Carpentry |  |  | 0 |  | 1500 | 1500 | 1500 | 0 | 1500 | 0 |  | 2096 | 596 | 71.56% | 1500 | 1500 | 0
20 | 28 | Window Trim and Casing (per window) | 11 |  | 0 |  | 500 | 500 | 500 | 0 | 500 | 0 |  | - | -
20 | 29 | Door Trim and Casing (per door) | 6 | 68 | 0 |  | 500 | 500 | 500 | 0 | 500 | 0 |  | - | -
20 | 30 | Baseboards (LF) | 265.705 | 2 |  | 1 | 500 | 500 | 500 | 0 | 500 | 0 |  | - | -
19 |  | Paint |  |  | 0 | 0 | 1866.9 | 1866.9 | 241.69 | 1625.21 | 176 | 66 |  | 4432 | 2565.1 | 51.35% | 2276 | 176 | 100 | 2000
19 | 31 | Interior (SF) | 3546 |  | 0 | 0.35 | 1241.1 | 1241.1 | 241.69 | 999.41 | 176 | 65.69 |  | - | -
19 | 32 | Exterior Deck, Beams, and Soffit (SF) | 1788 |  | 0 | 0.35 | 625.8 | 625.8 |  | 625.8 | 0 | 0 |  | - | -
29 |  | Mechanical |  |  | 0 |  | 500 | 500 | 0 | 500 | 0 | 0 |  | 1250 | 750 | 40% | 500 |  |  | 500
29 | 33 | New duct line from existing heater or electric baseboard | 1 | 300 | 0 | 500 | 500 | 500 |  | 500 | 0 | 0
27 |  | Plumbing |  |  | 4485 |  | 1800 | 6285 | 1404.94 | 4880.06 | 885 | 520 |  | 3950 | -2335 | 48.23% | 1905 | 885 | 520 | 500
27 | 34 | Gas pipe to Fireplace and Outdoor grill (~25') | 1 | 300 | 300 |  | 0 | 300 |  | 300 | 0 | 0 |  | - | -
27 | 35 | Master Bath - Relocate toilet 3' over | 1 | 550 | 550 |  | 0 | 550 |  | 550 | 0 | 0 |  | - | -
27 | 36 | Master Bath - New Shower plumbing and faucet | 1 | 550 | 550 | 300 | 300 | 850 |  | 850 | 0 | 0 |  | - | -
27 | 36.1 | Master Bath - New Bathtub plumbing, and faucet | 1 | 550 | 550 | 700 | 700 | 1250 |  | 1250 | 0 | 0 |  | - | -
27 | 37 | Master Bath - New Sink and faucets | 2 | 550 | 1100 | 150 | 300 | 1400 |  | 1400 | 0 | 0 |  | - | -
27 | 38 | (E) Downstairs Bath - Replumb pee-trap (currently there is none, easily accessible though) | 1 | 375 | 375 |  |  | 375 | 375 | 0 | 375 | 0 |  | - | -
27 | 38.1 | Snake (E) sink line |  |  | 135 |  |  | 135 | 135 | 0 | 135 | 0 |  | - | -
27 | 39 | Plumb water line to washer/dryer (~5' from existing line in exposed mechanical room) | 1 | 375 | 375 |  |  | 375 | 375 | 0 | 375 | 0 |  | - | -
27 | 40 | New - Kitchen Sink, faucet, and fridge water line | 1 | 550 | 550 | 500 | 500 | 1050 | 519.94 | 530.06 | 0 | 519.94 |  | - | -
27 | 41 | Garage utility sink and waterline | 1 | 550 | 0 | 150 | 0 | 0 |  | 0 | 0 | 0 |  | - | -
28 |  | Electrical |  | 0 | 0 |  | 2530 | 2530 | 4.1 | 2525.9 | 0 | 4 |  | 6985 | 4455 | 14.32% | 1000 |  |  | 1000
28 | 42 | Rough-Lights | 19 | 40 |  | 0 | 500 | 500 |  | 500 | 0 | 0 |  | - | -
28 | 43 | Rough-Outlets | 25 | 40 |  | 10 | 250 | 250 | 4.1 | 245.9 | 0 | 4.1 |  | - | -
28 | 44 | Rough-Stove |  | 75 |  |  | 300 | 300 |  | 300 | 0 | 0 |  | - | -
28 | 45 | Light Fixtures (re ceiling plans) | 17 | 35 |  | 40 | 680 | 680 |  | 680 | 0 | 0 |  | - | -
28 | 46 | New 200 amp panel and meter combo | 1 | 2500 |  |  | 800 | 800 |  | 800 | 0 | 0 |  | - | -
23 |  | Hardwoods |  |  | 0 |  | 2922.5 | 2922.5 | 0 | 2922.5 | 0 | 0 |  | 6137 | 3214.5 | 32.59% | 2000 |  |  | 2000
23 | 47 | Hardwood Floor | 1169 |  | 0 | 2.5 | 2922.5 | 2922.5 |  | 2922.5 | 0 | 0 |  | - | -
32 |  | Appliances |  |  |  |  | 850 | 850 | 0 | 850 | 0 | 0 |  | 1000 | 150 | 50% | 500 |  |  | 500
32 | 48 | Dishwasher | 1 |  |  |  | 500 | 500 |  | 500 | 0 | 0 |  | - | -
32 | 49 | Venta-hood/Microwave | 1 |  |  |  | 350 | 350 |  | 350 | 0 | 0 |  | - | -
11 |  | Landscaping |  |  | 3412.5 |  | 4364 | 7776.5 | 7776.39 | 0.11 | 7776 | 0.39 |  | 0 | -7776.5 | 100% | 10352 | 10352 | 0
| 50 | Retention walls/Landscaping | 1 |  | 0 | 1 | 0 | 0 |  | 0 |  | 0
11 | 51 | Fence | 650 | 5.25 | 3412.5 | 5.5 | 4364 | 7776.5 | 7776.39 | 0.11 | 7776 | 0.39 |  | 10352 | 2575.5 | 100% | 10352 | 10352
|  | Garage |  |  | 550 |  | 2328 | 2878 | 2904.32 | -26.11 | 2878 | 0 | 26.32 | 0 | -2878 | 0% | 0 |  | 0
| 52 | New Lights, insulation, drywall, framing, | 1 | 50 | 250 | 1083 | 1083 | 1332.89 | 1359 | -26.11 | 1333 | 0 | 26 | - | -
| 53 | New Slab 4" slab (SF) | 500 | 1 | 300 | 925 | 925 | 1225.09 | 1225.09 | 0 | 1225 | 0.09 |  | - | -
| 54 | Used potbelly stove and pipes or baseboard |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | - | -
| 55 | Built in Shelving |  |  |  | 320 | 320 | 320.23 | 320.23 | 0 | 320 | 0.23 |  | - | -
4 |  | Roof & Gutters |  |  | 0 |  | 8798.47 | 8798.47 | 8476.31 | 547.1 | 0 | 5710 | 2766.31 | 8945 | 146.53 | 94.41% | 8445 | 2807 | 5138 | 500
4 | 56 | Composite shingles, gutter (1388 SF) |  |  |  |  | 1962 | 1962 | 1414.9 | 547.1 | 0 | 391 | 1023.9 | - | -
4 | 57 | Roof SIPs(1388 SF) |  |  |  |  | 4836.47 | 4836.47 | 4836.47 | 0 | 0 | 4836.47 |  | - | -
4 | 57.1 | Boom Truck and fork lift rental |  |  |  |  | 2000 | 2000 | 2224.94 | -224.94 | 0 | 482 | 1742.94 | - | -
35 | 57.2/58 | Miscellaneous/Permit | [5 empty] | 350 | 350 | 0 | 0 | 350 |  | 4460 | 4110 | 100% | 4459.78 | 2093 | 2366.78
[11 empty] | 0 | 0
|  | Total |  |  | 19295.875 |  | 88084.5411 | 111084.4161 | 69627.36 | 39864.2061 | 27792 | 41835.36 | 14299.51 | 93819 | -17265.4161 |  | 66058.73 | 30888 | 20807.73 | 14363
| 59 | HUD draw fees |  |  |  |  | 150 | 0 |  | 0 |  | 0 |  | 750 | 750
| 60 | Contingincies/Add service | [5 empty] | 1949 |  | 1949 |  | 0 |  | 9436.68 | 7487.68 |  | 9436 | 2878 | 6558
|  | Total w/ Permit Hud fee and contingincies | [5 empty] | 111167.4161 | 69627.36 | 41813.2061 | 27792 | 41835.36 |  | 104005.68 | -7161.7361 |  | 75494.73 | 33766 | 27365.73 | 14363
[5 empty] | Amount Borrowed |  |  | 105000 | [7 empty] | 10% reserve | 7549.473 | 3376.6 | 2736.573 | 1436.3
|  | Amount over budget |  |  | Amount Saved/over |  |  | 4218.4161 | [7 empty] | Amount to me | 67945.257 | 30389.4 | 24629.157 | 12926.7
[16 empty] | Amount left | 29208.27
Account Balance 9/23
2906
15382.67
18288.67
3438
14850.67

## Schedule
|  |  |  | MAR 25-31 | [6 empty] | APR 1-7 | [6 empty] | APR 8-14 | [6 empty] | APR 15-21 | [6 empty] | APR 22-28 | [6 empty] | APR 29-MAY 5 | [6 empty] | MAY 6-12 | [6 empty] | MAY 13-19 | [6 empty] | MAY 20-26 | [6 empty] | MAY27-JUNE 2 | [6 empty] | JUNE 3-9 | [6 empty] | JUNE 10-16 | [6 empty] | JUNE 17-23 | [6 empty] | JUNE 24-30 | [6 empty] | JUL 1-7 | [6 empty] | JUL 8-14 | [6 empty] | JUL 15-21 | [6 empty] | JUL 22-28 | [6 empty] | JUL 29-AUG4 | [6 empty] | AUG5-AUG11 | [6 empty] | AUG 12-18 | [6 empty] | AUG 19-25 | [6 empty] | AUG 26- SEP1 | [6 empty] | SEP 2- SEP 8 | [6 empty] | SEP 9- SEP 15 | [6 empty] | SEP 16 SEP22 | [6 empty] | SEP 23 SEP29 | [6 empty] | SEP 30 OCT6 | [6 empty] | OCT7-OCT13 | [6 empty] | OCT 14-20 | [6 empty] | OCT21-OCT 27
TASK | Start Date | Complete Date | Weeks | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S | S | M | T | W | H | F | S
Garage-Phase 1 | 2012-03-18 | 2012-04-14 | Weeks: 3
Built in Shelving | bar: Weeks to MAR 25-31 S
New Slab 4" slab (SF) | bar: Weeks to MAR 25-31 S; MAR 25-31 S
New Lights,outlets,and insulation, and siding | bar: Weeks; APR 1-7 S; APR 1-7 H to MAY 13-19 S
Used potbelly stove and pipes | bar: Weeks; MAY 13-19 S
Disposal & Permits-Phase 1 | 2012-03-25 | 2012-05-19 | Weeks: 8
Variance Application (submitted 3/21) | 2012-03-21 | 2012-04-20 | bar: MAR 25-31 S; APR 1-7 S to APR 8-14 S; APR 15-21 S; APR 22-28 S to MAY 13-19 S
Permit Application | 2012-04-21 | 2012-04-21 | bar: MAY 13-19 S
Roll Out (disposal) |  | 2012-05-30 | bar: MAY 13-19 S
Professional Services-Phase 1 | 2012-04-01 | 2012-05-19 | Weeks: 7
Engineering, Permitting,HUD fees | bar: APR 1-7 S to APR 15-21 S; APR 22-28 S to MAY 13-19 S
Landscaping-Phase 2 | 2012-05-01 | 2012-04-21 | Weeks: 3
Fence | bar: APR 1-7 S to APR 15-21 S; APR 22-28 S
Tear down Barn for Siding and Trimwork | 2012-04-15 | 2012-05-19 | Weeks: 5
Tear down Barn wood | bar: APR 15-21 S to APR 29-MAY 5 S
Clean Barnwood | bar: MAY 6-12 S
Put up Barnwood siding in shop | bar: MAY 13-19 S
Foundation and Concrete work-Phase 1 | 2012-05-20 | 2012-06-02 | Weeks: 2
Addition Column 30''X30''X12'' CONC PAD w/ 16"x16" x 4' Pilasters | bar: MAY 20-26 S to MAY27-JUNE 2 S
Deck Colums pre-bored holes (LF) | bar: MAY 20-26 S to MAY27-JUNE 2 S
Wall Framing-Phase 1 | 2012-06-03 | 2012-06-16 | Weeks: 2; MAY 6-12 S: *; MAY 13-19 S: *; MAY 20-26 S: *; MAY27-JUNE 2 S: *
(Ext) wall (847 SF)2x6 Framing,sheathing,insulation, tar paper, Mtpl; (SF) | bar: JUNE 17-23 S to JUNE 24-30 S
(Int) wall (330 sf); 2x4 Framing (SF) | bar: JUNE 17-23 S to JUNE 24-30 S
6x6 Column (see take off) | bar: JUNE 17-23 S to JUNE 24-30 S
6x6 Beams (see take off) | bar: JUNE 17-23 S to JUNE 24-30 S
Column brackets (30),bases (14) and hardware | bar: JUNE 17-23 S to JUNE 24-30 S
Floor framing - ICF | bar: MAY 6-12 S; MAY 13-19 S; MAY 20-26 S; MAY27-JUNE 2 S; JUNE 17-23 S to JUNE 24-30 S
Fireplace box, and venting | bar: JUNE 17-23 S to JUNE 24-30 S
Fireplace framing and stone | bar: JUNE 17-23 S to JUNE 24-30 S
Roof & Gutters-Phase 1 | 2012-06-17 | 2012-06-23 | bar: Weeks; JUL 1-7 S
Roof Framing, insulation and deck (1388 SF) | bar: JUL 1-7 S
Composite shingles, gutter (1388 SF) | bar: JUL 1-7 S
Windows & Door Install-Phase 1 | 2012-06-24 | 2012-06-30 | bar: Weeks; MAY27-JUNE 2 S; JUNE 17-23 S; JUNE 24-30 S; JUL 1-7 S to JUL 8-14 S
Windows | bar: JUL 1-7 S to JUL 8-14 S
Interior Doors | bar: JUL 1-7 S to JUL 8-14 S
Exterior Door | bar: JUL 1-7 S to JUL 8-14 S
Mechanical-Phase 1 | 2012-06-24 | 2012-06-30 | bar: Weeks; JUL 1-7 S
New duct line from existing heater or electric baseboard | bar: JUL 1-7 S
Electrical-Phase 1 | 2012-07-01 | 2012-07-14 | Weeks: 2
Rough-Lights | bar: JUL 1-7 M to JUL 1-7 S; JUL 15-21 S to JUL 22-28 S
Rough-Outlets | bar: JUL 1-7 M to JUL 1-7 S; JUL 15-21 S to JUL 22-28 S
Rough-Stove | bar: JUL 1-7 M to JUL 1-7 S; JUL 15-21 S to JUL 22-28 S
Light Fixtures (re ceiling plans) | bar: JUL 1-7 M to JUL 1-7 S; JUL 15-21 S to JUL 22-28 S
New 200 amp panel and meter combo | bar: JUL 1-7 M to JUL 1-7 S; JUL 15-21 S to JUL 22-28 S
Plumbing-Phase 1 | 2012-07-17 | 2012-07-30 | Weeks: 2
(E) Downstairs Bath - Replumb pee-trap (currently there is none, easily accessible though) | bar: JUL 1-7 S to JUL 15-21 S
Plumb water line to washer/dryer (~5' from existing line in exposed mechanical room) | bar: JUL 1-7 S to JUL 15-21 S
New - Kitchen Sink, faucet, and fridge water line | bar: JUL 1-7 S to JUL 15-21 S
Garage utility sink and waterline | bar: JUL 1-7 S to JUL 15-21 S
Gas pipe to Fireplace and Outdoor grill (~25') | bar: JUL 1-7 S to JUL 15-21 S
Insulation-Phase 1 | 2012-07-15 | 2012-07-21 | bar: Weeks; JUL 29-AUG4 S
Drywall-Phase 1 | 2012-07-22 | 2012-07-28 | bar: Weeks; AUG5-AUG11 S
Walls and Ceilings (Hang Tape Mud per sheet)
Paint-Phase 1 | 2012-07-29 | 2012-08-04 | bar: Weeks; AUG 12-18 S
Interior (SF) | bar: AUG 12-18 S
Exterior Deck, Beams, and Soffit (SF) | bar: AUG 12-18 S
Hardwoods-Phase 1 | 2012-08-05 | 2012-08-11 | bar: Weeks; AUG 19-25 S to AUG 19-25 W
Hardwood Floor | bar: AUG 19-25 S to AUG 19-25 W
Cabinets-Phase 1 | 2012-08-12 | 2012-08-18 | bar: Weeks; JUL 22-28 S; JUL 29-AUG4 S; AUG5-AUG11 S; AUG 12-18 S; AUG 19-25 S; AUG 19-25 H to AUG 26- SEP1 S
Uppers (LF) | bar: AUG 19-25 H to AUG 26- SEP1 S
Lowers (LF) | bar: AUG 19-25 H to AUG 26- SEP1 S
Corian Countertops (LF) 44SF kitchen; 16 sf vanity
Appliances-Phase 1 | 2012-08-12 | 2012-08-18 | bar: Weeks; AUG 26- SEP1 S
Dishwasher
Venta-hood
Finish Carpentry-Phase 1 | 2012-08-19 | 2012-08-25 | bar: Weeks; SEP 2- SEP 8 S
Window Trim and Casing (per window) | bar: SEP 2- SEP 8 S
Door Trim and Casing (per door) | bar: SEP 2- SEP 8 S
Baseboards (LF) | bar: SEP 2- SEP 8 S
Disposal -Phase 2 | 2012-08-26 | 2012-09-01 | bar: Weeks; SEP 9- SEP 15 S
Roll Out (disposal)
Demolition (man/days)
Wall Framing-Phase 2 | 2012-09-02 | 2012-09-08 | bar: Weeks; SEP 16 SEP22 S
(Int) wall (330 sf); 2x4 Framing (SF) | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
(Ext) wall patch and tooth in siding where window is to be removed (SF) | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Re-insulate Ceiling above (e) cabin | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Plumbing - Phase 2 | 2012-09-02 | 2012-09-08 | bar: Weeks; SEP 16 SEP22 S
Master Bath - Relocate toilet 3' over | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Master Bath - New Shower plumbing and faucet | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Master Bath - New Bathtub plumbing, and faucet | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Master Bath - New Sink and faucets | 2012-09-02 | 2012-09-08 | bar: SEP 16 SEP22 S
Electrical-Phase 2 | 2012-09-02 | 2012-09-15 | Weeks: 2
Rough-Lights
Rough-Outlets
Rough-Stove
Light Fixtures (re ceiling plans)
Windows & Door Install - Phase 2 | 2012-09-16 | 2012-09-22 | bar: Weeks; SEP 30 OCT6 S
Windows | bar: SEP 30 OCT6 S
Interior Doors | bar: SEP 30 OCT6 S
Exterior Door | bar: SEP 30 OCT6 S
Drywall - Phase 2 | 2012-09-16 | 2012-09-22 | bar: Weeks; SEP 30 OCT6 S
Walls and Ceilings (Hang Tape Mud per sheet)
Walls and Ceilings (Texture per sheet)
Paint -Phase 2 | 2012-09-23 | 2012-09-29 | bar: Weeks; OCT7-OCT13 S
Interior (SF)
Tile-Phase 2 | 2012-09-23 | 2012-09-29 | bar: Weeks; OCT7-OCT13 S
Shower Tile and shower pan (200SF)
Floor Tile (SF)
Hardwoods-Phase 2 | 2012-09-30 | 2012-10-13 | Weeks: 2
Hardwood Floor | bar: OCT 14-20 S to OCT21-OCT 27 S
Finish Carpentry-Phase 2 | 2012-09-30 | 2012-10-13 | Weeks: 2
Window Trim and Casing (per window)
Door Trim and Casing (per door)
Baseboards (LF)
Deck and Outdoor Kitchen - Phase 2 | 2012-10-14 | 2012-10-27 | Weeks: 2
Outdoor kitchen concrete countertops (SF)
Built in outdoor grill
Exterior Deck Framing (SF)
Railings (LF)
Landscaping-Phase 2 | 2012-10-14 | 2012-10-27 | Weeks: 2
Retention walls/Landscaping
Contingency
Total |  |  | MAY 13-19 S: BY OTHERS
SELF PERFORM
[39 empty] | * | [13 empty] | LEAD TIME ITEMS

## Material Takeoff
BEAMS AND COLUMNS |  |  |  | WALLS, ROOF, and Fireplace | [5 empty] | FLOORS AND CEILINGS | [5 empty] | DOORS, WINDOWS AND IGU'S | [9 empty] | Kitchen and bath
Structural Column Schedule |  |  |  | Wall Schedule | [5 empty] | Floor and Deck Schedule | Area
Family and Type | Length | Board Size | [7 empty] | Floor: 10" JOIST AND DECK_EXTER | 193 |  |  |  |  | Curtain Panel Material Takeoff
[7 empty] | Existing Walls to be refinished |  |  | Floor: 10" JOIST AND DECK_EXTER | 385 | 578 |  |  |  | Material: Name | Material: Area | Height | Width |  | Mullion Schedule |  |  |  |  | Countertop Material Takeoff
Dimension Lumber-Column: 6x6 | 5' - 1" | 8 |  | 3" STONE 1/2" plywd -312 wd | 8 |  |  | 182 |  | Floor: 10" JOIST AND SUBSTRATE | 585 | 585 | [8 empty] | Type | Length |  |  |  | Family and Type | Length | Depth | Material: Area | Material: Name
Dimension Lumber-Column: 6x6 | 5' - 1" | 8 |  | 3" STONE 1/2" plywd -312 wd | 8 |  |  | 406 |  | Total | 1163 |  |  |  |  | Glass | 7 | 2' - 10 3/4" | 2' - 3 5/32"
Dimension Lumber-Column: 6x6 | 5' - 1" | 8 |  | 3" STONE 1/2" plywd -312 wd | 34 |  |  | 180 | [7 empty] | Glass | 4 | 1' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 2.51 | Counter Top: 24" Depth | 6.42 | 2' - 1" | 33 | Corian
Dimension Lumber-Column: 6x6 | 5' - 1" | 8 |  | 3" STONE 1/2" plywd -312 wd | 44 |  |  | 67 | [7 empty] | Glass | 14 | 2' - 10 3/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 5.03 | Counter Top: 24" Depth | 3.56 | 2' - 1" | 19 | Corian
Dimension Lumber-Column: 6x6 | 5' - 1" | 8 |  | 3" STONE 1/2" plywd -312 wd | 4 |  |  | 65 | [7 empty] | Glass | 4 | 1' - 8 1/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 1.83 | Counter Top: 24" Depth | 7.73 | 2' - 1" | 40 | Corian
Dimension Lumber-Column: 6x6 | 6' - 0" | 8 |  | 3" STONE 1/2" plywd -312 wd | 5 |  |  | 200 | [7 empty] | Glass | 8 | 1' - 8 1/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 1.77 |  | 2" x 4.5" rectangular | 4 | 06 40 00-Counter Top: 36" Depth No Splash | 8 | 3' - 0" | 51 | Corian
Dimension Lumber-Column: 6x6 | 6' - 0" | 8 |  | 3" STONE 1/2" plywd -312 wd | 19 |  |  | 227 | [7 empty] | Glass | 8 | 1' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 4.86 |  | 2" x 4.5" rectangular | 2 | Grand total: 4
Dimension Lumber-Column: 6x6 | 6' - 0" | 8 |  | 3" STONE 1/2" plywd -312 wd | 20 |  | Total sf | 1327 | [7 empty] | Glass | 8 | 3' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 2.26 | Total countertops and lower cabinets | 25.71
Dimension Lumber-Column: 6x6 | 6' - 0" | 8 |  | Total | 142 |  | Total sheets | 165.875 | [7 empty] | Glass | 18 | 3' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 1.83 |  | 2" x 4.5" rectangular | 4.78 | Uppers cabinets | 9.98
Dimension Lumber-Column: 6x6 | 8' - 0" | 8 | [13 empty] | Glass | 7 | 2' - 10 3/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 3.83 |  | 2" x 4.5" rectangular | 3.83
Dimension Lumber-Column: 6x6 | 9' - 6" | 10 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 14 | [10 empty] | Glass | 4 | 1' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.43 |  | 2" x 4.5" rectangular | 4.78
Dimension Lumber-Column: 6x6 | 9' - 6" | 10 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 14 | [10 empty] | Glass | 14 | 2' - 10 3/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 5.03 |  | 2" x 4.5" rectangular | 2.35
Dimension Lumber-Column: 6x6 | 11' - 6" | 12 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 23 | [10 empty] | Glass | 4 | 1' - 8 1/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 2.98 | Railing Schedule 2
Dimension Lumber-Column: 6x6 | 11' - 6" | 12 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 23 | [10 empty] | Glass | 8 | 1' - 8 1/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 1.94 |  | 2" x 4.5" rectangular | 1.77 | Length
Dimension Lumber-Column: 6x6 | 13' - 0" | 14 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 23 | [10 empty] | Glass | 8 | 1' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 3.15 |  | 2" x 4.5" rectangular | 4.86
Dimension Lumber-Column: 6x6 | 13' - 0" | 14 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 23 | [10 empty] | Glass | 8 | 3' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.26 |  | 2" x 4.5" rectangular | 2.35 |  | 7.54
Dimension Lumber-Column: 6x6 | 14' - 0" | 14 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 51 | [10 empty] | Glass | 18 | 3' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 1.83 |  | 7.11
Dimension Lumber-Column: 6x6 | 14' - 0" | 14 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 67 | [10 empty] | Glass | 7 | 2' - 10 3/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 1.94 |  | 2" x 4.5" rectangular | 3.83 |  | 7.11
Dimension Lumber-Column: 6x6 | 14' - 10" | 16 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 208 | [10 empty] | Glass | 4 | 1' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.51 |  | 2" x 4.5" rectangular | 2.43 |  | 7.54
Dimension Lumber-Column: 6x6 | 14' - 10" | 16 |  | Basic Wall: Exterior- 5.25"-Mp-6WS-GP | 346 | [10 empty] | Glass | 14 | 2' - 10 3/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 5.03 |  | 2" x 4.5" rectangular | 5.03 |  | 7.54
Dimension Lumber-Column: 6x6 | 14' - 10" | 16 |  | Total | 792 | [10 empty] | Glass | 4 | 1' - 8 1/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 1.83 |  | 2" x 4.5" rectangular | 2.98 |  | 7.54
Dimension Lumber-Column: 6x6 | 14' - 10" | 16 | [13 empty] | Glass | 8 | 1' - 8 1/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 4 |  | 2" x 4.5" rectangular | 1.94 |  | 7.54
Dimension Lumber-Column: 6x6 | 17' - 11 29/32" | 12 | [13 empty] | Glass | 8 | 1' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 2 |  | 2" x 4.5" rectangular | 3.15 |  | 4.18
|  | 8 |  | Basic Wall: Exterior- 5.25"-WS-4WS-GP | 9 | [10 empty] | Glass | 8 | 3' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.26 |  | 2" x 4.5" rectangular | 2.26 |  | 4.18
Dimension Lumber-Column: 6x6 | 23' - 7" | 16 |  | Basic Wall: Exterior- 5.25"-WS-4WS-GP | 11 | [10 empty] | Glass | 18 | 3' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 4.78 | Total | 60.28
|  | 8 |  | Basic Wall: Exterior- 5.25"-WS-4WS-GP | 16 | [10 empty] | Glass | 7 | 2' - 10 3/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 3.83 |  | 2" x 4.5" rectangular | 1.94
Dimension Lumber-Column: 6x6 | 23' - 7" | 16 |  | Basic Wall: Exterior- 5.25"-WS-4WS-GP | 19 | [10 empty] | Glass | 4 | 1' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 2.51
|  | 8 |  | Total | 55 | [10 empty] | Glass | 14 | 2' - 10 3/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 5.03
Dimension Lumber-Column: 6x6 | 23' - 7" | 16 | [13 empty] | Glass | 4 | 1' - 8 1/4" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 1.83 | Window Schedule
|  | 8 | [13 empty] | Glass | 8 | 1' - 8 1/4" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 1.77 |  | 2" x 4.5" rectangular | 4 | Type Mark | Height | Width | Sill Height
Dimension Lumber-Column: 6x6 | 23' - 7" | 16 |  | Basic Wall: Foundation - BWG - 8CC | 13 | [10 empty] | Glass | 8 | 1' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 4.86 |  | 2" x 4.5" rectangular | 2
|  | 8 |  | Basic Wall: Foundation - BWG - 8CC | 16 | [10 empty] | Glass | 8 | 3' - 9" | 2' - 3 5/32" |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 2.26 | A | 3' - 3" | 3' - 3" | 3' - 3"
Dimension Lumber-Column: 6x6 | 23' - 7" | 16 |  | Basic Wall: Foundation - BWG - 8CC | 30 | [10 empty] | Glass | 18 | 3' - 9" | 4' - 9 11/32" |  | 2" x 4.5" rectangular | 1.83 |  | 2" x 4.5" rectangular | 4.78 | A | 2' - 9" | 2' - 3" | 4' - 3"
|  | 8 |  | Basic Wall: Foundation - BWG - 8CC | 36 | [10 empty] | Glass | 12 | 2' - 10 3/4" | 4' - 2 1/2" |  | 2" x 4.5" rectangular | 3.83 |  | 2" x 4.5" rectangular | 3.83 | A | 3' - 3 1/2" | 4' - 11" | 3' - 3 1/2"
|  |  |  | Basic Wall: Foundation - BWG - 8CC | 39 | [10 empty] | Glass | 24 | 5' - 8" | 4' - 2 1/4" |  | 2" x 4.5" rectangular | 2.43 |  | 2" x 4.5" rectangular | 3.35 | A | 2' - 5" | 2' - 3" | 3' - 3"
|  |  |  | Total | 134 | [10 empty] | Glass | 24 | 5' - 8" | 4' - 2 1/4" |  | 2" x 4.5" rectangular | 5.03 |  | 2" x 4.5" rectangular | 4.29 | A | 3' - 3" | 3' - 3" | 2' - 3"
Structural Beam Framing Schedule | [15 empty] | Glass | 10 | 2' - 7 5/8" | 3' - 10" |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 2.3 | A | 3' - 3" | 3' - 3" | 2' - 3"
Family and Type | Length | [14 empty] | Glass | 10 | 2' - 7 5/8" | 3' - 10" |  | 2" x 4.5" rectangular | 1.94 |  | 2" x 4.5" rectangular | 2.55 | A | 3' - 3" | 1' - 6" | 2' - 3"
[16 empty] | Glass | 19 | 2' - 10 3/4" | 6' - 6" |  | 2" x 4.5" rectangular | 3.15 |  | 2" x 4.5" rectangular | 4.19 | A | 3' - 3" | 1' - 6" | 2' - 3"
Timber: 6x8 | 6' - 2" | 8 | [13 empty] | Glass | 11 |  |  |  | 2" x 4.5" rectangular | 2.26 |  | 2" x 4.5" rectangular | 4.19 | A | 3' - 3" | 3' - 3" | 3' - 3"
Timber: 6x8 | 7' - 6 1/2" | 8 | [13 empty] | Glass | 8 |  |  |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 6
Timber: 6x8 | 7' - 6 1/2" | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 12 | [10 empty] | Glass | 4 |  |  |  | 2" x 4.5" rectangular | 1.94 |  | 2" x 4.5" rectangular | 6
Timber: 6x8 | 7' - 6 1/2" | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 17 | [10 empty] | Grand total: 41 |  |  |  |  | 2" x 4.5" rectangular | 2.51 |  | 2" x 4.5" rectangular | 4.19
Timber: 6x8 | 7' - 6 1/2" | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 27 | [10 empty] | Total | 406 |  |  |  | 2" x 4.5" rectangular | 5.03 |  | 2" x 4.5" rectangular | 4.19
Timber: 6x8 | 31' - 1" | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 36 | [15 empty] | 2" x 4.5" rectangular | 1.83 |  | 2" x 4.5" rectangular | 6
|  | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 39 | [15 empty] | 2" x 4.5" rectangular | 4 |  | 2" x 4.5" rectangular | 6
|  | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 41 | [10 empty] | Baseboard Schedule |  |  |  |  | 2" x 4.5" rectangular | 2 |  | 2" x 4.5" rectangular | 3.83
|  | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 55 | [10 empty] | Type | Length |  |  |  | 2" x 4.5" rectangular | 2.26 |  | 2" x 4.5" rectangular | 3.83
Timber: 6x8 | 10' - 1 3/8" | 12 |  | Basic Wall: Interior - PAR/1-312-1 | 103 | [15 empty] | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 2.97
Timber: 6x8 | 10' - 1 3/8" | 12 |  | Total | 330 | [10 empty] | WD-BASE | 16.99 |  |  |  | 2" x 4.5" rectangular | 3.83 |  | 2" x 4.5" rectangular | 2.97
Timber: 6x8 | 8' - 0" | 8 | [13 empty] | WD-BASE | 11.5 |  |  |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 3.83
Timber: 6x8 | 23' - 2" | 8 | [13 empty] | WD-BASE | 14.5 |  |  |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 3.83
|  | 8 |  | Mp-tyvek-1/2" plywd-6WS--6" batt - 1/2" GP | 792 | [10 empty] | WD-BASE | 2.33 |  |  |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 2.97
|  | 8 |  | WS-tyvek-1/2" plywd-4WS-GP | 55 | [10 empty] | WD-BASE | 5.42 |  |  |  | 2" x 4.5" rectangular | 1.77 |  | 2" x 4.5" rectangular | 2.97
Timber: 6x8 | 8' - 0" | 8 |  | Basic Wall: Interior - PAR/1-312-1 | 330 | [10 empty] | WD-BASE | 3.5 |  |  |  | 2" x 4.5" rectangular | 4.86 |  | 2" x 4.5" rectangular | 4.55
|  |  |  | Total | 1177 | [10 empty] | WD-BASE | 32.06 |  |  |  | 2" x 4.5" rectangular | 2.35 |  | 2" x 4.5" rectangular | 6.67
[16 empty] | WD-BASE | 4.69 |  |  |  | 2" x 4.5" rectangular | 1.83 |  | 2" x 4.5" rectangular | 2.98
[16 empty] | WD-BASE | 10.63 |  |  |  | 2" x 4.5" rectangular | 3.83 |  | 2" x 4.5" rectangular | 6.81
|  |  |  | Roof Schedule | [11 empty] | WD-BASE | 10.17 |  |  |  | 2" x 4.5" rectangular | 2.43 |  | 2" x 4.5" rectangular | 4.42
|  |  |  | Family and Type | Area | [10 empty] | WD-BASE | 8.58 |  |  |  | 2" x 4.5" rectangular | 5.03 |  | 2" x 4.5" rectangular | 3.06
|  |  |  | Basic Roof: Wood Rafter 6" - Asphalt | 390 | [10 empty] | WD-BASE | 26.88 |  |  |  | 2" x 4.5" rectangular | 2.98 |  | 2" x 4.5" rectangular | 1.16
|  |  |  | Basic Roof: Wood Rafter 6" - Asphalt Shingle - Insulated 2 | 437 | [10 empty] | WD-BASE | 14.88 |  |  |  | 2" x 4.5" rectangular | 1.94 |  | 2" x 4.5" rectangular | 3.15
|  |  |  | Basic Roof: Wood Rafter 4" - Asphalt Shingle - Insulated | 66 | [10 empty] | WD-BASE | 27.12 |  |  |  | 2" x 4.5" rectangular | 3.15 |  | 2" x 4.5" rectangular | 4.21
|  |  |  | Basic Roof: Wood Rafter6" - Asphalt Shingle - Insulated 3 | 495 | [10 empty] | WD-BASE | 14.4 |  |  |  | 2" x 4.5" rectangular | 2.26 |  | 2" x 4.5" rectangular | 6.5
|  |  |  | Grand total: 4 | [11 empty] | WD-BASE | 30.17 |  |  |  | 2" x 4.5" rectangular | 4.78 |  | 2" x 4.5" rectangular | 1.63
[5 empty] | 1388 | [10 empty] | WD-BASE | 7.73 |  |  |  | 2" x 4.5" rectangular | 1.94
[16 empty] | Total | 241.55 |  |  |  | TOTAL |  |  |  | 427.59
|  |  |  | Ceiling Schedule | [11 empty] | Total x1.10 | 265.705
|  |  |  | Compound Ceiling: GPDW | 51
|  |  |  | Compound Ceiling: GPDW | 512
|  |  |  | Compound Ceiling: GPDW | 149
712
TOTALS
Door Schedule
Treated Columns | QTY | Cost/per | Price | Fireplace and outdoor Kitchen | QTY | Cost Per | Total x1.10 | [8 empty] | Door # |  | Location | Leaves | Width | Height | Comments | Type Mark | Cost Per
6x6x8 | 14 | 24 | 336 | STONE Countertop base (SF) | 50 | 20 | 1100
6x6x10 | 2 | 30 | 60 | 3" Concrete Countertop (SF) | 35 | 10 | 385 | [8 empty] | 101A | 101 | MASTER BEDROOM |  | 6' - 0" | 6' - 8" | Biparting Sliding Door | 3 | 250
6x6x12 | 2 | 36 | 72 | Built in Gas Grill | 1 | 800 | 800 | [8 empty] | 101B | 102 | MASTER CLOSET | SGL | 2' - 6" | 6' - 8" | Closet Door | 1 | 125
6x6x14 | 4 | 42 | 168 | 3" Stone on 1/2" plywd on 3 1/2 WS | 100 | 8 | 880 | [8 empty] | 101C | 103 | MASTER BATH | SGL | 2' - 0" | 6' - 8" | Bathroom locking door | 1 | 125
6x6x16 | 9 | 27 | 243 | See through fire place and flue | 1 |  | 6154.82 | [8 empty] | 101D | 104 | SHOWER/TUB | SGL | 2' - 0" | 6' - 8" | Glass Shower Door | 4 | 160
Total | 31 |  | 879 | Total |  |  | 9319.82 | [8 empty] | 101E | 101 | MASTER BEDROOM | SGL | 2' - 6" | 6' - 8" | Bedroom locking door | 1 | 125
[16 empty] | 105 | 105 | VESTIBULE |  | 3' - 0" | 6' - 8" | Entry Vestibule door | 2 | 500
Treated Beams | QTY | Cost/per | Price | [12 empty] | 106 | 105 | VESTIBULE | SGL | 2' - 0" | 6' - 8" | Closet Door | 1 | 125
Timber: 6x8x8 | 14 | 24 | 336 | Walls | [11 empty] | Grand total: 7 | [7 empty] | 1410
Timber: 6x8x12 | 2 | 36 | 72 | Mp-tyvek-1/2" plywd-6WS--6" batt - 1/2" GP (793 SF) | [18 empty] | plus tax | 1551
Total | 16 |  | 408 | WS-tyvek-1/2" plywd-4WS-GP (55SF)
|  |  |  | Interior - PAR/1-312-1 (330SF) | QTY | Cost Per | Total x1.10
Column Hardware | QTY | Cost/per | Price | Metal Panel | 792 | 1.25 | 1089
|  |  |  | Wood Siding patch | 100 | 2 | 200
6x6 Column Bases | 14 | 20 | 280 | 2x6x8 | 29 | 4 | 127.6
Column Brackets | 30 | 50 | 1500 | 2x6x10 | 56 | 5 | 308
Total |  |  | 1780 | 2x8x8 Header | 6 | 5.5 | 36.3
|  |  |  | 2x4x8 | 80 | 3 | 264 |  |  |  |  | Size | QTY |  | Concrete/per | Concrete
Concrete Pads | QTY | Cost/per | Price | Fiberglass Insulation (SF) | 792 | 0.4 | 348.48 |  |  |  | Bigfoots
16''X16''X4' PILASTERS | 14 | 137.95 | 1931.3 | Tyvek House Wrap | 792 | 155 per 150 sf | 900 |  |  |  |  | 28 | 2 |  | 0.079 | 0.158
30''X30''X12'' CONC PADS | 14 | 117.28 | 1641.92 | J-trim- 8ft | 37 | 3.9 | 158.73 | 2496.21 |  |  |  | 24 | 7 |  | 0.058 | 0.406
PUMP PADS AND PILASTERS | 1 | 1000 | 1000 | 1/2" x4x8 plywood sheathing | 28 | 8.5 | 261.8 |  |  |  |  | 20 | 10 |  | 0.04 | 0.4
Deck Drilled Piers | 14 | 50 | 700 | Nails,glue, etc |  |  | 400 |  |  |  | Sauna tubs |  |  |  |  | 0
Total |  |  | 5273.22 | Total |  |  | 4093.91 |  |  |  | 4' | 16 | 12 | 4 | 0.181 | 2.172
[12 empty] | 14 | 5 | 2 | 0.139 | 0.695
|  |  |  | Drywall Sheets/tape/mud/screws | QTY | Cost Per | Total x1.10 |  |  |  |  | 12 | 15 | 5 | 0.102 | 1.53
|  |  |  | Walls (1507 sf) | 41.8611 | 8 | 368.3778 |  |  |  |  | 10 | 6 | 2 | 0.071 | 0.426
|  | Timber Budget |  | Ceiling (712 sf) | 19.7778 | 8 | 174.0444 | [8 empty] | 5.787
|  |  |  | Total | 61.6389 |  | 542.4222 | [8 empty] | 6.3657
636.57
|  |  |  | Roof | [6 empty] | Rebar
|  |  |  | 2x10x24 | 19 | 24 | 456 |  | 780 |  | #4 - 12' | 53
|  |  |  | 2x6x14 | 28 | 7 | 196 |  |  |  | Rebar and Sauna tubs | 1350
|  |  |  | 2x8x18 | 1 | 5.5 | 5.5 |  |  |  | Concrete | 800
|  |  |  | 2x4x8 | 65 | 3 | 195 |  |  |  | Pump truck | 511
|  |  |  | T1-11 plywood | 11 | 25 | 275 |  |  |  | Bobcat Rental | 874
|  |  |  | 1/2" OSB | 24 | 8.5 | 204 |  |  |  | Excavation | 1250
|  |  |  | Metal Panel (390SF) | 4 | 100 | 400 |  |  |  | Dirt | 715 | 480
|  |  |  | Asphalt Shingles (1047SF) | 11 | 90 | 990 |  |  |  | Labor | 2000
|  |  |  | 6" Rigid Insulation | 29 | 80 | 2320 |  |  |  | Auger Rental | 100
|  |  |  | Tarpaper | 4 | 18 | 72 |  |  |  | Total | 7600
|  |  |  | Nails, flashing, gutter, fascia, etc |  |  | 500
|  |  |  | Total |  |  | 5613.5
|  |  |  | Framing |  |  | 3651.5
|  |  |  | Roofing |  |  | 1962
|  |  |  | Existing Siding | 991.1